## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status | Acceptance Criteria | Tasks/Comments
S1 | S1 | US-001 | Environment Setup & Repository Initialization | MUST HAVE | VS Code, Git | Shlok Gautam | Completed | Repo initialized with README, .gitignore; basic folder structure setup. | Setup repo, add initial docs, configure git hooks.
S1 | S1 | US-002 | Setup Development Environment & Dependencies | MUST HAVE | Python 3.8+, pip | Shlok Gautam | Completed | Virtual environment active; dependencies in requirements.txt installed. | Create venv, requirements, install packages.
S2 | S2 | US-003 | Integrate Google News API Data Fetching | MUST HAVE | GNews Client, API keys | Shlok Gautam | Completed | Pull news articles by search query; data frame structured correctly. | API key management, fetch loop, error handling.
S2 | S2 | US-004 | Integrate Twitter API for Recent Tweets | MUST HAVE | Tweepy, Twitter API keys | Shlok Gautam | Completed | Fetch recent tweets matching keywords and store in DF. | Pagination, user mapping, rate-limit handling.
S3 | S3 | US-005 | Implement VADER Sentiment Analysis for News Data | MUST HAVE | NLTK, pandas | Shlok Gautam | Completed | Sentiment scores and labels added to news data frame. | Install nltk, mocking for tests.
S3 | S3 | US-006 | Implement VADER Sentiment Analysis for Twitter Data | MUST HAVE | NLTK, pandas | Shlok Gautam | Completed | Sentiment analysis integrated for tweets similarly. | Create reusable sentiment functions.
S4 | S4 | US-007 | Normalize, Concatenate, and Clean Data | MUST HAVE | pandas, numpy | Shlok Gautam | Completed | Unified data with consistent schema; missing data handled. | Timestamp parsing & timezone normalization.
S4 | S4 | US-008 | Aggregate Sentiment Data into Time Buckets | MUST HAVE | pandas | Shlok Gautam | Completed | Aggregated metrics (mean sentiment, count) per hour/day with smoothing window applied. | Implement rolling averages, z-score computations.
S5 | S5 | US-009 | Develop Sentiment Forecasting using Prophet | SHOULD HAVE | Prophet | Shlok Gautam | Completed | Produce sentiment forecasts with confidence bounds. | Model fitting, future frame prediction, visualization prep.
S6 | S6 | US-010 | Build Interactive Streamlit Dashboard Layout | MUST HAVE | Streamlit, plotly | Shlok Gautam | Completed | Dashboard with sidebar controls, tabbed views, responsive charts. | Design UX/UI, implement navigation, data binding.
S6 | S6 | US-011 | Implement Real-time Alerts for Sentiment & Volume Spikes | MUST HAVE | Slack API, requests | Shlok Gautam | Completed | Alerts triggered and sent via Slack webhook integration. | Define alert rules, threshold sliders, test webhook message format.
S7 | S7 | US-012 | Add CSV Download Buttons for Raw, Combined, Aggregated, Forecast Data | COULD HAVE | Streamlit | Shlok Gautam | Completed | User able to export datasets as CSV files from each dashboard view. | Implement Streamlit download feature, optimize CSV conversion.
S7 | S7 | US-013 | Add Cache & Data Refresh Mechanism | SHOULD HAVE | Streamlit cache | Shlok Gautam | Completed | Data refresh on-demand with caching to reduce API calls and speed interface. | Use decorators, manage cache invalidation.
S8 | S8 | US-014 | Improve Error Handling & Logging for API Requests | SHOULD HAVE | Python logging | Shlok Gautam | Completed | Graceful handling of API errors, retries, and logging for diagnostics. | Add logging, retry logic, fallback defaults.
S8 | S8 | US-015 | Add Keyword Trend Analysis & Visualization | SHOULD HAVE | pandas, plotly | Shlok Gautam | Completed | Keywords extracted, counted, visualized with spikes and z-scores. | Keyword regex matching, plotly line charts.
S9 | S9 | US-016 | Write Comprehensive Documentation & Developer Guide | MUST HAVE | Markdown, ReadTheDocs | Shlok Gautam | Completed | Full README and guides for setup, use, and contribution available. | Document code, API usage, environment setup and dashboard walkthrough.
S9 | S9 | US-017 | Conduct Unit & System Integration Tests | MUST HAVE | pytest, streamlit | Shlok Gautam | Completed | Tests created, run automatically in CI environment. | Write unit tests for key modules; setup test suite.
S10 | S10 | US-018 | Set up CI/CD for Deployment to Streamlit Sharing or Cloud | MUST HAVE | GitHub Actions, dotenv | Shlok Gautam | Completed | Successful build and deployment workflow with environment variables protected. | Configure workflows, secrets, deployment scripts.
S10 | S10 | US-019 | Perform Final User Acceptance Testing and Feedback Incorporation | MUST HAVE | User feedback | Shlok Gautam | Planned | User feedback collected and addressed prior to final release. | Schedule demo sessions, collect bugs/improvements, document fixes.

## Sprint Backlog
User Story ID | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Estimated Hours
US-001 | T1 | Environment setup (Python, VS Code, Git setup) | 2025-08-21 | 2025-08-23 | Shlok Gautam | Setup | Completed | 2
US-002 | T2 | Connect and test NewsAPI | 2025-08-23 | 2025-08-25 | Shlok Gautam | API Integration | Completed | 3
US-009 | T3 | Establish Twitter API client and token verification | 2025-08-24 | 2025-08-26 | Shlok Gautam | API Setup | Completed | 3
US-003 | T4 | Data collection and cleaning of AI/ML news articles | 2025-08-25 | 2025-08-28 | Shlok Gautam | Data Collection & Cleaning | Completed | 5
US-010 | T5 | Twitter data fetch and preprocessing | 2025-08-27 | 2025-08-30 | Shlok Gautam | Data Handling | Completed | 4
US-004 | T6 | Sentiment analysis using VADER and Gemini API | 2025-09-01 | 2025-09-07 | Shlok Gautam | Sentiment Processing | Completed | 5
US-011 | T7 | Validation and tuning of sentiment models | 2025-09-06 | 2025-09-10 | Shlok Gautam | Model Tuning | Completed | 3
US-005 | T8 | Forecast sentiment trends with Prophet | 2025-09-11 | 2025-09-15 | Shlok Gautam | Forecasting | Completed | 4
US-012 | T9 | Automate sentiment forecasting schedule | 2025-09-14 | 2025-09-17 | Shlok Gautam | Automation | Completed | 3
US-006 | T10 | Slack alert system integration | 2025-09-18 | 2025-09-21 | Shlok Gautam | Alerts Setup | Completed | 3
US-013 | T11 | Configure alert thresholds and escalation rules | 2025-09-20 | 2025-09-23 | Shlok Gautam | Alert Configuration | Completed | 2
US-007 | T12 | Design Streamlit dashboard with visuals | 2025-09-24 | 2025-09-30 | Shlok Gautam | Frontend Development | Completed | 5
US-014 | T13 | Integrate interactive charts and filters in dashboard | 2025-09-28 | 2025-10-03 | Shlok Gautam | UI Enhancements | Completed | 4
US-008 | T14 | Final integration, testing and deployment | 2025-10-04 | 2025-10-07 | Shlok Gautam | System Testing | Completed | 4

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | API key missing in .env | Added NEWSAPIKEY, GEMINIAPIKEY, Slack credentials to .env
Sprint 1 | Day 3 | Errors while fetching NewsAPI articles | Debugged query syntax and pagination; successfully fetched 500 AI/ML articles
Sprint 2 | Day 14 | RSS feed parsing returned empty | Fixed BeautifulSoup XML parsing limited items per feed
Sprint 2 | Day 15 | Gemini API rate limit exceeded | Applied subset sentiment analysis for scheduled batch processing
Sprint 3 | Day 27 | Slack notifications failing | Verified Slack token and channel ID, tested send alert function
Sprint 3 | Day 29 | Forecast anomalies unclear | Added threshold logic for trend detection; visualized recent vs. historical mean
Sprint 4 | Day 37 | Pivot tables and visualizations misaligned | Created pivot tables for sentiment, mentions, and share of voice
Sprint 4 | Day 40 | Alert and anomaly detection complex | Implemented IsolationForest anomaly detection and alert table

## Retrospection
Sprint | Start Date | End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | 2025-08-21 | 2025-08-25 | Shlok Gautam | Set up Python environment, configure API keys | Manually cleaning unstructured data | Using .env for secure API key storage | Successfully collected initial dataset and cleaned CSV for downstream tasks
Sprint 2 | 2025-09-03 | 2025-09-10 | Shlok Gautam | Aggregate news from multiple sources, integrate Gemini API for sentiment | Using single-source news only | Using LLMs for sentiment classification | Combined RSS and NewsAPI articles, filtered AI-related content
Sprint 3 | 2025-09-15 | 2025-09-23 | Shlok Gautam | Implement trend forecasting with Prophet, configure Slack alerts | Manually monitoring trends | Automating sentiment detection and alerts | Forecasted sentiment trends, sent automated Slack alerts
Sprint 4 | 2025-09-25 | 2025-10-05 | Shlok Gautam | Build Streamlit dashboard with interactive filters and visualizations | Static visualizations only | Using matplotlib/seaborn and anomaly detection | Deployed interactive Strategic Intelligence Dashboard